## Sheet1
| ID | Stack Rank | Priority | Severity | State | Title
| 2958 |  | 2 | 3 - Medium | Active | ( Manage Tasks ) - Summary count required for fields coming from Manage Permits
| 3126 |  | 2 | 3 - Medium | Active | (Manage Clients) - Caption should be 'Billing Contact Phone #' instead of 'Billing Phone #'
| 3100 |  | 2 | 3 - Medium | Active | (Manage Jobs) - Alert should be shown while clicking 'Delete' button without selecting any record
| 3224 |  | 2 | 3 - Medium | Active | (Manage Permits) - Data should not sort while sorting 'View/Edit' column
| 3294 |  | 2 | 2 - High | Active | (Manage Permits) - Error when adding duplicate DOT tracking# for 'Unknown' Project
| 3236 |  | 2 | 3 - Medium | Active | (Manage Permits) - Filter row should not be shown in the exported PDF file
extra column is remvoed | 3234 |  | 2 | 3 - Medium | Active | (Manage Permits) - Issues in the exported excel sheet
| 3292 |  | 2 | 3 - Medium | Active | (Manage Permits) - 'Permit Status' field showing blank while setting status 'Active' with expires date greater than expiring 5 days
| 3240 |  | 2 | 3 - Medium | Active | (Manage Permits) - Permit Type alignment
| 3244 |  | 2 | 3 - Medium | Active | (Manage Permits) - plain text for column level filters
| 3286 |  | 2 | 3 - Medium | Active | (Manage Permits) - Project ID has entries as 'Unkhown' instead of 'Unknown'
| 3222 |  | 2 | 3 - Medium | Active | (Manage Permits) - Proper selected rejected reason should be shown instead of id in the 'Rejected Reason' field
| 3293 |  | 2 | 3 - Medium | Active | (Manage Permits) - State gets highlighted when Project ID set to 'Unknown'
| 3291 |  | 2 | 3 - Medium | Active | (Manage Permits) - The Expire Date do not get highlighted when Status is selected
| 3250 |  | 1 | 3 - Medium | Active | (Manage Permits/ Dailies) - Warning error with invalid date entered
| 3209 |  | 2 | 3 - Medium | Active | (Manage Tasks) - Jobs with all statuses should show on the screen
| 2818 |  | 1 | 2 - High | Active | Manage Jobs, Add/Update Job & Manage Tasks: Only active projects should be populated in 'Project ID' dropdown for the filter section & popups
| 2854 |  | 1 | 2 - High | Active | Manage Jobs: Delete button is missing on the screen to delete job record(s)
| 2793 |  | 1 | 3 - Medium | Active | Manage Jobs: Summary row should be added at the top of the grid
| 2966 |  | 1 | 3 - Medium | Active | Manage Users & Clients: Cell background color should be white instead of gray while focusing drop-down fields
| 2814 |  | 1 | 2 - High | Active | Manage Users: On user creation, no email is generated.
| 2791 |  | 1 | 3 - Medium | Active | Manage Users: Sorting is not working properly for Company column
| 2784 |  | 1 | 3 - Medium | Active | Menu: Layout issues
| 2878 |  | 1 | 2 - High | Active | Update Job: Save button is not working while entering/editing date fields of the popup